## Frontend Defects
Defect ID | Title | Description | Area | Assignee | Status | Resolution
D001 | Document upload validation | Unsupported file type or invalid upload state could affect the document-upload flow. | Document Upload | Kurangi Bala Venkatarao | Resolved | Added frontend file-type validation and upload-state feedback for PDF, DOCX, TXT and CSV.
D002 | Upload/API status feedback | Users needed clear feedback while documents were being processed by the backend. | Document Upload/API | Kurangi Bala Venkatarao | Resolved | Added progress/loading, success and error states in the upload UI.
D003 | Query response structure | Frontend needed to handle the updated M2 /query response containing answer, sources, confidence and retrieval data. | Chat/API Integration | Kurangi Bala Venkatarao | Resolved | Updated response handling and mapped the new backend fields to the chat interface.
D004 | AI answer display | Generated backend answers were not displayed consistently in the chat interface. | Chat UI | Kurangi Bala Venkatarao | Resolved | Displayed the backend-generated answer as the primary chat response.
D005 | Source and citation display | RAG source references needed to be visible to support transparent answers. | RAG Transparency | Kurangi Bala Venkatarao | Resolved | Added source/citation and retrieved-context presentation.
D006 | Confidence/relevance display | Relevance and confidence information needed a consistent frontend representation. | RAG Transparency | Kurangi Bala Venkatarao | Resolved | Added confidence and relevance values to the response/context UI.
D007 | Empty retrieval results | Zero retrieval results could leave an incorrect or stale context panel visible. | Context Inspector | Kurangi Bala Venkatarao | Resolved | Cleared the context panel when retrieval results are empty while keeping the backend answer visible.
D008 | Conversation memory flow | Follow-up queries needed to stay connected to the correct conversation. | Conversation UI | Kurangi Bala Venkatarao | Resolved | Integrated conversation_id into the frontend query flow and conversation history.
D009 | Clarification response flow | Clarification questions needed a clear way for users to submit additional information. | Chat UI | Kurangi Bala Venkatarao | Resolved | Added clarification display and response handling in the chat interface.
D010 | Voice transcript integration | Speech input needed to enter the same query workflow as typed input. | Voice UI | Kurangi Bala Venkatarao | Resolved | Connected Web Speech API transcripts to the normal /query flow.
D011 | Read Aloud citation handling | Citation markers should not be unnecessarily spoken during voice output. | Voice UI | Kurangi Bala Venkatarao | Resolved | Adjusted Read Aloud content handling so citation markers are excluded from spoken text.
D012 | Knowledge Gap dashboard rendering | Knowledge-gap API records needed to be presented clearly in the frontend. | Analytics UI | Kurangi Bala Venkatarao | Resolved | Integrated Knowledge Gap APIs and displayed missing-coverage records, categories and statistics.

## Defect Summary
Category | Count | Status
Document Upload | 2 | Resolved
Chat/API Integration | 2 | Resolved
RAG Transparency | 2 | Resolved
Context Inspector | 1 | Resolved
Conversation/Clarification | 2 | Resolved
Voice UI | 2 | Resolved
Analytics UI | 1 | Resolved