## Frontend Work Log
Day | Milestone | Frontend Activity | Work Completed | Progress
Day 1 | M1 | React frontend structure and RAG interaction | Set up the React frontend structure and created the basic layout for document upload and RAG interaction. | 30%
Day 2 | M1 | Document upload UI | Implemented the document upload UI with file selection and supported PDF, DOCX, TXT and CSV formats. | 50%
Day 3 | M1 | Upload status and validation feedback | Added upload status/progress feedback and success/error messages for document processing. | 65%
Day 4 | M1 | Knowledge-base interface integration | Improved the document upload and knowledge-base interface and verified frontend-to-backend integration. | 80%
Day 5 | M1 | Upload workflow testing | Tested the complete upload workflow and fixed UI/API integration issues. | 90%
Day 6 | M1 | Frontend validation | Completed frontend validation for document upload, processing status and basic RAG testing interface. | 100%
Day 1 | M2 | Query response flow | Reviewed the M2 API response structure and prepared the frontend query flow for displaying AI responses and retrieval results. | 30%
Day 2 | M2 | FastAPI query integration | Connected the query input with the FastAPI /query endpoint and handled the basic request/response flow. | 45%
Day 3 | M2 | AI answer display | Implemented display of generated AI answers and basic query status/loading states. | 60%
Day 4 | M2 | Sources and retrieved context | Added source/citation and retrieved-context display for RAG responses. | 75%
Day 5 | M2 | Relevance and confidence display | Added relevance/confidence information and improved the presentation of retrieved chunks in the UI. | 85%
Day 6 | M2 | Complete query-flow testing | Tested the complete frontend query flow and verified that answer, source and retrieval information were displayed correctly. | 95%
Day 7 | M2 | Response/error handling | Fixed frontend response-display issues and improved error/loading handling during RAG queries. | 100%
Day 1 | M3 | M3 frontend requirements | Reviewed M3 frontend requirements for conversation memory, clarification, voice interaction and transparency display. | 25%
Day 2 | M3 | Conversation memory | Added conversation creation and connected the frontend with conversation_id for memory-enabled queries. | 40%
Day 3 | M3 | Clarification flow | Updated the chat flow to display clarification questions and allow users to submit clarification responses. | 55%
Day 4 | M3 | Conversation history | Integrated conversation history/follow-up queries into the chat interface and verified contextual responses. | 70%
Day 5 | M3 | Voice input | Integrated browser-based Web Speech API voice input and connected the generated transcript to the normal /query flow. | 80%
Day 6 | M3 | Read Aloud and citations | Added/verified Read Aloud using the browser Speech Synthesis API and improved citation/source display during voice interaction. | 90%
Day 7 | M3 | Feature integration testing | Tested memory, clarification, voice and transparency features together and fixed frontend integration issues. | 95%
Day 8 | M3 | Voice/citation UI refinement | Improved chat UI behavior for citations and Read Aloud, ensuring citation markers were not unnecessarily spoken in voice output. | 97%
Day 1 | M4 | Knowledge-gap patterns | Studied query patterns and identified how unanswered, low-confidence, and zero-retrieval queries can indicate missing knowledge-base coverage. | 30%
Day 2 | M4 | Knowledge-gap UI structure | Designed the frontend structure to display knowledge-gap information and identified the required backend analytics data. | 50%
Day 3 | M4 | Knowledge Gap API integration | Integrated the frontend with the Knowledge Gap APIs and displayed detected missing-coverage records in the UI. | 65%
Day 4 | M4 | Dashboard categories and statistics | Added UI handling for knowledge-gap categories, statistics, and frequently occurring unanswered queries. | 80%
Day 5 | M4 | Knowledge-gap testing | Tested API responses and frontend rendering for unanswered, zero-retrieval, and low-confidence query patterns; fixed integration issues. | 90%
Day 6 | M4 | Dashboard validation | Completed frontend validation of the Knowledge Gap Dashboard, ensuring query patterns and missing knowledge-base coverage were clearly presented to users. | 100%

## Sprint Backlog
Task ID | Milestone | Task Description | Team Member | Activity | Status | Progress
M1-T01 | M1 | Set up React frontend and document-upload layout | Kurangi Bala Venkatarao | Frontend | Completed | 100%
M1-T02 | M1 | Implement PDF, DOCX, TXT and CSV upload selection | Kurangi Bala Venkatarao | Frontend | Completed | 100%
M1-T03 | M1 | Add upload progress, success and error states | Kurangi Bala Venkatarao | Frontend | Completed | 100%
M1-T04 | M1 | Validate knowledge-base upload and integration flow | Kurangi Bala Venkatarao | Frontend/API Integration | Completed | 100%
M2-T01 | M2 | Integrate FastAPI /query response structure | Kurangi Bala Venkatarao | Frontend/API Integration | Completed | 100%
M2-T02 | M2 | Display AI answer, sources and retrieval results | Kurangi Bala Venkatarao | Chat UI | Completed | 100%
M2-T03 | M2 | Display relevance and confidence information | Kurangi Bala Venkatarao | RAG Transparency | Completed | 100%
M2-T04 | M2 | Handle empty retrieval, errors and loading states | Kurangi Bala Venkatarao | Frontend | Completed | 100%
M3-T01 | M3 | Integrate conversation_id and memory-enabled queries | Kurangi Bala Venkatarao | Conversation UI | Completed | 95%
M3-T02 | M3 | Implement clarification question/response flow | Kurangi Bala Venkatarao | Chat UI | Completed | 95%
M3-T03 | M3 | Integrate Web Speech API voice input | Kurangi Bala Venkatarao | Voice UI | Completed | 95%
M3-T04 | M3 | Integrate Read Aloud and citation-safe voice output | Kurangi Bala Venkatarao | Voice UI | Completed | 95%
M4-T01 | M4 | Design Knowledge Gap Dashboard UI | Kurangi Bala Venkatarao | Analytics UI | Completed | 100%
M4-T02 | M4 | Integrate Knowledge Gap APIs | Kurangi Bala Venkatarao | Frontend/API Integration | Completed | 100%
M4-T03 | M4 | Display unanswered, zero-retrieval and low-confidence patterns | Kurangi Bala Venkatarao | Analytics UI | Completed | 100%

## Stand up Meeting
Milestone | Day | Impediment | Action Taken | Team Member
M1 | Day 1 | Frontend flow and upload structure needed to be organized. | Set up React components and defined the document-upload/RAG interaction flow. | Kurangi Bala Venkatarao
M1 | Day 4 | Frontend-to-backend upload integration needed verification. | Verified upload states, document information and API responses in the UI. | Kurangi Bala Venkatarao
M2 | Day 2 | Updated /query response contained answer, sources and retrieval data. | Adjusted frontend response handling to consume the new response structure. | Kurangi Bala Venkatarao
M2 | Day 5 | Retrieved chunks and confidence needed clearer presentation. | Improved source, relevance, confidence and context display. | Kurangi Bala Venkatarao
M3 | Day 3 | Clarification and follow-up queries needed to remain in the same conversation. | Connected clarification and follow-up actions with conversation_id. | Kurangi Bala Venkatarao
M3 | Day 5 | Voice transcript needed to follow the normal query path. | Connected Web Speech API transcript to the existing /query flow. | Kurangi Bala Venkatarao
M4 | Day 3 | Knowledge-gap records needed a clear frontend representation. | Integrated Knowledge Gap APIs and created missing-coverage UI. | Kurangi Bala Venkatarao
M4 | Day 5 | Different unanswered-query patterns needed consistent rendering. | Tested zero-retrieval, unanswered and low-confidence states and fixed UI integration issues. | Kurangi Bala Venkatarao

## Retrospection
SL # | Milestone | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | M1 | Kurangi Bala Venkatarao | Start validating upload states early. | Stop testing only after the full upload flow. | Continue reusable React components and clear user feedback. | Added validation, progress and success/error states during the upload workflow.
2 | M2 | Kurangi Bala Venkatarao | Start checking new backend response fields during integration. | Stop assuming the old response structure. | Continue transparent source and retrieval presentation. | Updated the UI for answer, sources, confidence and retrieved context.
3 | M3 | Kurangi Bala Venkatarao | Start testing memory, clarification and voice together. | Stop treating each chat feature as an isolated flow. | Continue using the existing query path for consistency. | Integrated conversation_id, clarification, Web Speech API and Read Aloud.
4 | M4 | Kurangi Bala Venkatarao | Start testing analytics states with realistic query patterns. | Stop showing empty or stale dashboard information. | Continue clear frontend visualization of backend analytics. | Validated unanswered, zero-retrieval and low-confidence knowledge-gap patterns.